## Weekly Task Log
ITS364 Weekly Task Log for Group 4 | [5 empty] | Member Attendance
Week # | Date | Task # | Main Task Description | Task Status | Additional Tasks, Notes, etc. | MG | JH | DP | JS | DV
1 | 2018-01-15 | 1 | Re-establish ITS360 group & review req., eerd, data dict., etc. | Complete | 6th Member added but dropped course in 2nd week | [5 empty] | MG = Michelle Gutierrez
| 2018-01-17 | 1 | Research & discuss potential technologies for DMCS | Initiated | JS: MySQL + PHP; JH: MySQL + WordPress
[5 empty] | DP: MySQL + ASP; MG: MySQL workbench; DV: WAMP/XAMP | [5 empty] | JH = Jose Huizar
2 | 2018-01-22 | 1 | Review EERD & delegate tables to members for CREATE table scripts | Complete | JS: Req/Social Media/Phone Calls/Website
[5 empty] | DV: Person/Volunteer/Client/Employee/Donor | [5 empty] | DP = Dhruvkumar Patel
JH: Proj/Enc; MG: Groups/Location; DP: Tasks/Skills
|  | 2 | Finalize decisions of which technologies to use to implement DMCS | Complete | [6 empty] | JS = Jeremy Savage
| 2018-01-24 | 1 | Create Win10 VM (Donn) | Complete
|  | 2 | Start writing CREATE TABLE scripts | Initiated | [6 empty] | DV = Donn Villaruz
3 | 2018-01-29 | 1 | Continue CREATE TABLE scripts | In-Progress
|  | 2 | Install WAMP/WordPress on Win10 VM (Donn) | Complete
| 2018-01-31 | 1 | Continue CREATE TABLE scripts | In-Progress
4 | 2018-02-05 | 1 | Continue CREATE TABLE scripts | In-Progress | Issues with Win10VM, so Jose tries to fix it
| 2018-02-07 | 1 | Continue CREATE TABLE scripts | In-Progress
|  | 2 | Create new Win10 VM (Jose) | Complete | Could not resolve VM issues
5 | 2018-02-12 | 1 | Finish CREATE TABLE scripts | Complete | JH starts designing wireframes
|  | 2 | Start writing INSERT scripts | Initiated | JH continues designing wireframes
| 2018-02-14 | 1 | Re-engineer EERD & MySQL database (Dhru, Michelle, Donn) | Initiated | New associative tables added
|  | 2 | Continue INSERT scripts | In-Progress | JH continues designing wireframes
6 | 2018-02-19 | 1 | Continue INSERT scripts | In-Progress | JH continues designing wireframes
| 2018-02-21 | 1 | Finish INSERT scripts | Complete
|  | 2 | Updated data dictionary & EERD (Dhru, Michelle, Donn) | Complete | JH continues designing wireframes
|  | 3 | List STORED PROCedures & begin assigning (Donn, Michelle) | Initiated
7 | 2018-02-26 | 1 | Review STORED PROC list & Delegate tables to members | Complete | DP: Person/Employee/Donor/Client/Encounter/Disaster
DV: Vol/Skills/Vol_Skills/Vol_Groups/Vol_Tasks
MG: Grp_Loc/Grps/Loc/Grp_Tasks/Tasks/Warehouse/Prod
JH: Warehouse_Prod/Proj_Location/Proj
JS: Req/Social_Media/Phone_Call/Website/Prod_Req
|  | 2 | Start writing STORED PROC scripts | Initiated | JH continues designing wireframes
| 2018-02-28 | 1 | Continue STORED PROC scripts | In-Progress | DV: Fixed/Updated EERD in MySQL Workbench
8 | 2018-03-05 | 1 | Continue STORED PROC scripts; | In-Progress | Start developing stored proc template (DV)
| 2018-03-07 | 1 | Continue STORED PROC scripts | In-Progress | Completed stored proc template (DV)
9 | 2018-03-12 | 1 | Spring Break -- Continue STORED PROC scripts | Optional | Recommended to continue tasks if desired
| 2018-03-14 | 1 | Spring Break -- Continue STORED PROC scripts | Optional | Recommended to continue tasks if desired
10 | 2018-03-19 | 1 | Continue STORED PROC scripts | In-Progress
| 2018-03-21 | 1 | Continue STORED PROC scripts | In-Progress | JH continues designing wireframes
11 | 2018-03-26 | 1 | Compile member STORED PROC scripts (DV) | Initiated | Team lab (3-4) compiled & updated by MG
|  | 2 | Start developing screen prototypes (MG, JH, DP, JS) | Initiated | Technologies used: XAMP, PHP/MySQL/JS/jQuery/HTML
| 2018-03-28 | 1 | Continue compiling member STORED PROC scripts (DV) | In-Progress | Team lab (5) compiled & updated by MG
|  | 2 | Continue developing prototypes (MG, JH, DP, JS) | In-Progress
12 | 2018-04-02 | 1 | Continue compiling member STORED PROC scripts (DV) | In-Progress | Proj: JH, Vol: DP, Tasks: DV, Grp: MG, Req: JS
|  | 2 | Continue developing screens (MG, JH, DP, JS) | In-Progress
| 2018-04-04 | 1 | Finish compiling member STORED PROC scripts (DV) | Complete | STORED PROC for Warehouse/Product completed by MG
|  | 2 | Continue developing prototypes (MG, JH, DP, JS) | In-Progress | Team lab (5) updated by MG
13 | 2018-04-09 | 1 | Continue developing prototypes (MG, JH, DP, JS) | In-Progress | Team lab (5) updated by MG
|  | 2 | Finishing tested member STORED PROC scripts (MG, DV) | Complete
| 2018-04-11 | 1 | Continue developing prototypes (all) | In-Progress | Updated MySQL database (MG)
14 | 2018-04-16 | 1 | Continue developing prototypes (all) | In-Progress | Updated MySQL database (DV)
| 2018-04-18 | 1 | Continue developing prototypes (all) | In-Progress | Updated MySQL database (DV)
15 | 2018-04-23 | 1 | Continue developing prototypes (all) | In-Progress | Updated MySQL database (DV)
Requirements updated by MG
| 2018-04-25 | 1 | Continue developing prototypes (all) | In-Progress
16 | 2018-04-30 | 1 | Final Black-box testing of dmcs web application (DV) | Complete | Updated MySQL database (DV)
|  | 2 | Update EERD, requirements, Data Dictionary, take Screenshots | Complete
|  | 3 | Live demo with instructor | Complete
Note on D2: Unless specifically noted, listed tasks apply to all group members
Note on G14: Absence notification received. Member is aware of her assigned task(s).
Note on G22: Absence notification received. Member is aware of her assigned task(s).
Note on J23: Absence notification received. Member is aware of his assigned task(s).
Note on H32: Absence notification received. Member is aware of his assigned task(s).
Note on I38: Absence notification received. Member is aware of his assigned task(s).
Note on J42: Absence notification received. Member is aware of his assigned task(s).
Note on G43: Absence notification received. Member is aware of her assigned task(s).
Note on G50: Absence notification received. Member is aware of her assigned task(s).
Note on H51: Absence notification received. Member is aware of his assigned task(s).
Note on J51: Absence notification received. Member is aware of his assigned task(s).